## sprint backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | 1 | Collected Aadhaar and non-Aadhaar document images and organized them into structured datasets for preprocessing, OCR testing, and fraud validation. | 2025-12-05 | 2025-12-10 | everyone | finding dataset | done | 12 hrs | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2; Day 6: 2
SPRINT 2
2 | 2 | Performed comprehensive image preprocessing including resizing, denoising, sharpening, and deskewing to improve document clarity and OCR accuracy. | 2025-12-11 | 2025-12-15 | SHIVANSHU | finding appropriate technique to extract data from image | done | 10hrs | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2
SPRINT 3
3 | 3 | Performed comprehensive image preprocessing including resizing, denoising, sharpening, and deskewing to improve document clarity and OCR accuracy. | 2025-12-15 | 2025-12-17 | SHIVANSHU | rule based validation to compare Aadhar QR data and OCR extracted fields | done | 7hrs | Day 1: 2; Day 2: 3; Day 3: 2
SPRINT 4
4 | 4 | Implemented Tesseract OCR to extract textual information from Aadhaar card images and generated structured outputs containing key identity fields such as Aadhaar/VID, Date of Birth, and Gender. | 2025-12-15 | 2025-12-16 | SHIVANSHU | I used a transfer learning to predict fake aadhaar, non_Aadhaar, fake_Aadhaar | done | 5hrs | Day 1: 2.5; Day 2: 2.5
SPRINT 5
5 | 5 | Performed face extraction from Aadhaar photo and live/person image for comparison. Applied face-matching logic to verify identity consistency when the document is classified as a real Aadhaar. | 2025-12-27 | 2025-12-27 | SHIVANSHU | I used a pretrained model to extract a face from two image and outputed whether both image match | done | 3
SPRINT 6
6 | 6 | Designed an ML model that takes OCR data, QR validation results, and image forensics inputs. The model produces a final Real/Fake classification with confidence-based fraud risk assessment. | 2025-12-17 | 2025-12-18 | SHIVANSHU | I used the Random forest classification model which is trained on the output of ocr which is in json format and these json files data is extracted into the csv file and then the model got trainied on the dataset with the f1 score 0.9 | done | 12 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2; Day 6: 2
SPRINT 7
7 | 7 | Developed OCR post-processing logic to clean extracted text, normalize formats, and handle real-world noise such as misread characters and spacing issues. | 2026-01-01 | 2026-01-02 | SHIVANSHU | manage in correct flow during to integration | done | 8hrs | Day 1: 4; Day 2: 4
SPRINT 8
8 | 8 | Designed and implemented a rule-based fraud detection engine to validate Aadhaar document authenticity by checking: Aadhaar / VID number format Date of Birth format validity Presence and consistency of mandatory fields Missing or inconsistent identity data | 2025-12-27 | 2026-01-03 | SHIVANSHU | Tested API ,working flow and Frontend part | done | 25hrs | Day 1: 4; Day 2: 5; Day 3: 4; Day 4: 3; Day 5: 3; Day 6: 3; Day 7: 2; Day 8: 2
Note on D1: ====== ID#AAABySIrxJc Please enter the dates in either of these formats (2026-01-06 15:39:39) 9/15/2016 or 15-Sep-2016
Note on E1: ====== ID#AAABySIrxIw Please enter the dates in either of these formats (2026-01-06 15:39:39) 9/15/2016 or 15-Sep-2016
Note on I2: ====== ID#AAABySdK7Mk Sumeet Kumar Barua08 (2026-01-06 15:39:39) This is the total task estimated in hours for all the user stories
Note on J2: ====== ID#AAABySIrxJY Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 1 work
Note on K2: ====== ID#AAABySIrxI4 Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 2 work
Note on L2: ====== ID#AAABySIrxJA Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 3 work
Note on M2: ====== ID#AAABySIrxIo Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 4 work
Note on N2: ====== ID#AAABySIrxJQ Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 5 work
Note on O2: ====== ID#AAABySIrxJM Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 6 work
Note on P2: ====== ID#AAABySIrxIs Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 7 work
Note on Q2: ====== ID#AAABySIrxI0 Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 8 work
Note on R2: ====== ID#AAABySdK7Mg Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 9 work
Note on S2: ====== ID#AAABySIrxIk Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 10 work
Note on T2: ====== ID#AAABySIrxJE Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 11 work
Note on U2: ====== ID#AAABySIrxI8 Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 12 work
Note on V2: ====== ID#AAABySIrxJI Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 13 work
Note on W2: ====== ID#AAABySIrxJU Sumeet Kumar Barua08 (2026-01-06 15:39:39) Pending effort hours after completion of day 14 work

## standup meetings
Sprint | Day | Impediments | Action Taken
1 | 2025-12-09 | unable to get fake data | we generated fake data
2 | 2025-12-14 | difficulty to get good ocr extraction | we used paddle ocr which gave far better results
3
4
5
6
7
8

## retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-12-05 | 2025-12-10 | everyone | we started with kaggle and google search
2 | 2 | 2025-12-11 | 2025-12-15
3 | 3
4 | 4
5 | 5 | 2025-12-27 | 2025-12-27
6 | 6
7 | 7
8 | 8

## product backlog
Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 |  | Data Collection & Dataset Preparation |  | used google, kaggle,fake images generated for dataset, and preprocessing done using python libraries | everyone
2 |  | Image Preprocessing Implementation |  | Implemented image preprocessing techniques using OpenCV, including resizing, denoising, sharpening, and deskewing to enhance document quality. | Shivanshu
3 |  | OCR-Based Data Extraction |  | Integrated Tesseract OCR to extract textual information from Aadhaar card images. | Shivanshu
4 |  | OCR Post-Processing & Validation Logic |  | Developed text-cleaning and normalization logic to correct common OCR errors and formatting issues. | Shivanshu
5 |  | Fraud Detection Logic |  | Designed a rule-based fraud detection engine to classify documents as REAL or SUSPICIOUS based on extracted data consistency. | Shivanshu
6 |  | End-to-End Pipeline Integration |  | Integrated image preprocessing, OCR extraction, and rule-based validation into a single end-to-end fraud detection pipeline. | Shivanshu
7 |  | Web Application & API Development |  | Developed a Flask-based backend API to handle Aadhaar image uploads and fraud verification requests. | Shivanshu
8 |  | Tested the complete pipeline with multiple Aadhaar scenarios including genuine, tampered, and fake samples. Validated system accuracy, reduced false positives, and ensured readiness for cloud-based deployment. and ui part made |  | Tested the complete system with genuine Aadhaar samples, low-quality images, rotated documents, and non-Aadhaar documents. | Shivanshu
Note on E1: ====== ID#AAABySIrxIg Sumeet Kumar Barua08 (2026-01-06 15:39:39) Mention the US ID(s) on which the user story depends.